## Tasks
Day | Resource | High-level task | Status | Detailed activities | Deliverable / goal
Day 1 | Ritu (Underwriting/domain) | Define underwriting scope & packet template |  | Choose underwriting scenario (e.g., term life new business). Describe where in the existing underwriting workflow the decision packet will be used (initial review/triage). Independently design the decision packet structure: sections for case summary, key medical risk factors, non-medical factors, missing info list, risk flags, recommended action, and rationale. | One-page use-case description. Decision packet v1.0 template (Markdown/Word + JSON schema) stored in a shared folder.
Day 1 | Monica (Python/Claude workflow) | Sandbox project setup | Completed | In the sandbox, create a Python project structure with folders for raw_docs, processed_text, packets, and config. Implement a simple script that scans case folders and logs available documents per case without needing business logic. Test one basic Claude call from Python to confirm connectivity. | Working repo in sandbox, minimal ingestion script, successful test call to Claude.
Day 1 | Salman (POC coordinator/eval) | Evaluation design & tracking sheet | Completed | Design evaluation criteria independently: coverage of key facts, correctness of risk flags, clarity of rationale, underwriting usefulness. Create an Excel sheet with columns for case ID, packet version, scores (1–5) per dimension, and free-text comments. You can assume any reasonable criteria; alignment can happen later but is not required to start. | Evaluation rubric and Excel scoring template created and saved.
Day 2 | Ritu | Underwriting data-to-packet mapping |  | Review sample medical records and underwriting data. List which medical and non-medical attributes are important to underwriting (age, smoker status, diagnoses, labs, financials, occupation). Map these attributes to packet sections in a standalone document so that any technical workflow can later reference it without needing back-and-forth. | Field-to-packet mapping document (e.g., attribute → packet section → priority).
Day 2 | Monica | Ingestion & text extraction pipeline | Completed | Build Python scripts to extract text from available medical records and underwriting docs (PDF/Word/text). Tag each chunk with case ID and document type (application, APS, labs, etc.). Produce a consolidated case_bundle JSON/dict per case. This can be done without waiting for underwriting rules; focus only on technical ingestion. | Script that returns a structured case_bundle for a given case ID and stores bundles in processed_text/.
Day 2 | Salman | Select golden cases for evaluation | Completed | Independently scan available data and pick 5–10 cases with varying complexity (simple, medium, complex). For each case, add a short textual note in Excel: “Expected decision type (e.g., Standard/Preferred/Postpone)” and a few key risk drivers as you understand them. You don’t need perfect underwriting accuracy; these are baseline expectations. | List of golden cases with baseline notes in the evaluation sheet.
Day 3 | Ritu | Create underwriting examples for ideal packets |  | For 3–4 selected cases, manually write short “ideal” decision packet content: key facts list, missing info list, and a concise rationale paragraph. Work purely in Word/Markdown or Excel; no need to know the exact Claude prompt. These examples will later be used for tuning but you can produce them independently. | Example packets for 3–4 cases (ideal manual versions) stored as documents.
Day 3 | Monica | Design Claude prompts for extraction | Completed | Using the case_bundle structure, design a Claude prompt that outputs JSON: key fields, missing information, risk flags. You can assume generic risk concepts (e.g., chronic conditions, lab abnormalities) using your own judgment or public underwriting notions. Implement a Python function extract_case_features(case_bundle) that calls Claude and parses the result. No need to wait for Resource A’s exact rules; keep prompts generic but structured. | Extraction prompt v1 and working Python function returning structured features.
Day 3 | Salman | Design Claude prompts for summarization & rationale |  | Create a second prompt that generates a case summary, list of highlighted risk factors, missing info, and a draft recommended action with a confidence indicator. Ensure it follows a fixed section structure consistent with packet v1.0, but you can assume a reasonable structure yourself. Implement generate_decision_narrative(extracted_features, case_bundle). | Narrative prompt v1 and Python function producing summary + rationale text sections.
Day 3 | Salman | Versioning and logging design |  | Define a simple versioning scheme for packets: caseID_packet_v1, v2, etc. Decide on a logging format (CSV or small DB) capturing case ID, prompt version, timestamp, and evaluator name. Set up an initial log file or table in Excel; you don’t need code integration yet. | Versioning scheme document and initial log template.
Day 4 | Ritu | Independent review of first AI packets |  | Once Resource B has generated a few packets, review them and annotate issues: missing critical facts, misinterpreted details, unclear rationale. You can do this offline in Word/Excel, marking each section with comments and desired improvements. This review doesn’t require changes in code; focus on underwriting quality. | Annotated packets for at least 5 cases, with comments per section.
Day 4 | Monica | End-to-end packet assembly |  | Integrate extraction and narrative outputs into a single packet object that matches the template (or your own assumed template). Create a function generate_packet(case_id) that runs ingestion, Claude extraction, and narrative generation, then returns structured data and a human-readable report (Markdown or HTML). | Working end-to-end function that produces packets for multiple cases and saves them to packets/.
Day 4 | Monica | Minimal UI or report view |  | Build a simple way to view packets: either a basic web UI (Flask/Streamlit) or HTML/Markdown reports opened in a browser or viewer. UI only needs navigation by case ID and section headings; no complex interactivity. | Minimal interface or report format to display full packets.
Day 4 | Salman | Initial evaluation run |  | Using the evaluation sheet, independently score AI-generated packets for the golden cases. Rate coverage, correctness, clarity, and usefulness on your 1–5 scale. Add qualitative comments for each case, without needing to coordinate edits with A or B. | Evaluation scores and comments for at least 5–10 packets in Excel.
Day 5 | Ritu | Underwriting guidance refinement |  | Based on your earlier annotations, produce a standalone “underwriting guidance for AI” document: which factors are must-have, which phrasing is preferred, and what typical decisions look like by risk pattern. This can be written without direct changes to prompts—just a document B can later consume. | Refined underwriting guidance doc for AI packets.
Day 5 | Monica | Prompt tuning iteration |  | Independently refine prompts by: emphasizing critical fields, requiring evidence-backed statements, and reducing overconfident language. Use your own analysis of packet failures plus generic underwriting knowledge. Regenerate packets for golden cases and store them as v2. | Updated prompts (v2) and regenerated packets (v2) for golden cases.
Day 5 | Salman | Before/after comparison in Excel |  | Compare v1 and v2 packets using the evaluation sheet. Add side-by-side scores and compute simple deltas (e.g., average coverage improvement). Create any charts (bar, line) in Excel to visualize improvement; this can be done without further input from A or B. | Updated evaluation sheet with v1 vs v2 metrics and charts.
Day 6 | Ritu | Demo storyline from underwriter perspective |  | Write a narrative describing the current underwriting workflow, pain points, and how the decision packet POC improves speed and consistency. Prepare a script for walking through one hero case during the demo (before: manual review; after: AI packet + human decision). This can be done based on your own view plus sample packets, without deep tech details. | Demo script and talking points focused on underwriter experience.
Day 6 | Monica | Code stabilization and runbook |  | Clean up code, add basic error handling and configuration (e.g., prompt version switches, case list). Write a short runbook describing how to run generate_packet for demo cases and how to refresh packets if needed. No need for editorial input from A/C—focus on making the tech easy to operate. | Stable POC codebase and runbook document.
Day 6 | Salman | Slide deck and Excel artifacts |  | Build a slide deck with: problem statement, solution overview, architecture diagram, screenshots of packets, and evaluation metrics. Use your Excel charts and tables to show quality improvements and potential business impact (e.g., time saved, consistency). | Completed demo deck and supporting Excel file with metrics and visuals.
Day 7 | Ritu | Final content polish |  | Review demo slides and hero packets for underwriting accuracy and clarity of narrative. Suggest minor edits (phrasing, emphasis) that you can apply yourself to the slides and script. | Polished underwriting narrative in deck and script.
Day 7 | Monica | Demo environment validation |  | Run end-to-end tests for chosen demo cases: ingestion, Claude calls, packet generation, UI display. Fix minor issues (paths, configuration) as needed. Confirm the runbook matches actual steps. | Validated demo environment ready for live run.
Day 7 | Salman | Full demo rehearsal notes |  | Conduct at least one rehearsal (even alone), timing the flow and noting any confusing transitions. Document final sequence of steps and who speaks when (if presenting as a team). Adjust slides order or emphasis based on rehearsal notes. | Demo rehearsal notes and final presentation sequence.

## Framework
Factor | Condition / band | Raw score | Weight | Weighted contribution (Raw Score * Weight) | Interpretation
Age | Best-fit age band for product (20-30) | 0 | 2 | 0 | Most favorable age band
Age | Slightly outside best-fit band (35-45) | 1 | 2 | 2 | Mildly adverse
Age | Moderately adverse band (45-55) | 2 | 2 | 4 | Requires closer review
Age | Strongly adverse band (55-60) | 3 | 2 | 6 | Materially adverse
Tobacco use | Never smoker / no nicotine | 0 | 3 | 0 | Best outcome
Tobacco use | Former smoker, remote quit | 1 | 3 | 3 | Mild adverse effect
Tobacco use | Former smoker, recent quit | 2 | 3 | 6 | Moderate adverse effect
Tobacco use | Current smoker / nicotine user | 3 | 3 | 9 | Strong adverse factor
BMI / build | Preferred range | 0 | 2 | 0 | No concern
BMI / build | Mildly outside preferred | 1 | 2 | 2 | Small increase in risk
BMI / build | Moderately outside preferred | 2 | 2 | 4 | Meaningful concern
BMI / build | Severely outside preferred | 3 | 2 | 6 | Strong concern
Blood pressure | Normal / controlled | 0 | 2 | 0 | No concern
Blood pressure | Mildly elevated but controlled | 1 | 2 | 2 | Minor issue
Blood pressure | Repeated elevated readings / moderate control issues | 2 | 2 | 4 | Needs review
Blood pressure | Uncontrolled / severe | 3 | 2 | 6 | Major concern
Diabetes | None | 0 | 3 | 0 | No concern
Diabetes | Diet controlled / mild | 1 | 3 | 3 | Mild concern
Diabetes | Oral meds, stable | 2 | 3 | 6 | Moderate concern
Diabetes | Insulin-dependent or poorly controlled | 3 | 3 | 9 | Major concern
Heart disease | None | 0 | 3 | 0 | No concern
Heart disease | Minor history, stable | 1 | 3 | 3 | Mild concern
Heart disease | Established disease, stable | 2 | 3 | 6 | Moderate concern
Heart disease | Recent event / significant disease | 3 | 3 | 9 | Major concern
Cancer history | None | 0 | 3 | 0 | No concern
Cancer history | Remote history, in remission | 1 | 3 | 3 | Mild concern
Cancer history | Recent treatment completed | 2 | 3 | 6 | Moderate concern
Cancer history | Active / recurrent / metastatic | 3 | 3 | 9 | Major concern
Respiratory disease | None | 0 | 2 | 0 | No concern
Respiratory disease | Mild, controlled asthma | 1 | 2 | 2 | Minor concern
Respiratory disease | Moderate COPD/asthma/sleep apnea | 2 | 2 | 4 | Moderate concern
Respiratory disease | Severe or oxygen-dependent | 3 | 2 | 6 | Major concern
Kidney/liver disease | None | 0 | 3 | 0 | No concern
Kidney/liver disease | Mild abnormality, stable | 1 | 3 | 3 | Mild concern
Kidney/liver disease | Chronic stable disease | 2 | 3 | 6 | Moderate concern
Kidney/liver disease | Advanced / progressive disease | 3 | 3 | 9 | Major concern
Mental health / substance use | None | 0 | 2 | 0 | No concern
Mental health / substance use | Remote, stable history | 1 | 2 | 2 | Mild concern
Mental health / substance use | Recent treatment or unstable | 2 | 2 | 4 | Moderate concern
Mental health / substance use | Recent hospitalization / active issue | 3 | 2 | 6 | Major concern
Medications | Few routine meds | 0 | 1 | 0 | Low concern
Medications | Multiple chronic meds | 1 | 1 | 1 | Mild supporting signal
Medications | Several high-risk meds / complex regimen | 2 | 1 | 2 | Moderate supporting signal
Medications | Very heavy regimen with complications | 3 | 1 | 3 | Strong supporting signal
Lab abnormalities | Normal labs | 0 | 2 | 0 | No concern
Lab abnormalities | Mild outlier | 1 | 2 | 2 | Minor concern
Lab abnormalities | Moderate abnormality | 2 | 2 | 4 | Meaningful concern
Lab abnormalities | Severe abnormality | 3 | 2 | 6 | Major concern
Recent hospitalization | None | 0 | 3 | 0 | No concern
Recent hospitalization | Older hospitalization, resolved | 1 | 3 | 3 | Mild concern
Recent hospitalization | Recent, but minor issue | 2 | 3 | 6 | Moderate concern
Recent hospitalization | Recent and serious | 3 | 3 | 9 | Major concern
Family history | None or irrelevant | 0 | 1 | 0 | No concern
Family history | Some relevant history | 1 | 1 | 1 | Mild concern
Family history | Strong early family history | 2 | 1 | 2 | Moderate concern
Family history | Strong hereditary pattern | 3 | 1 | 3 | Major concern
Occupation / avocation | Low hazard | 0 | 1 | 0 | No concern
Occupation / avocation | Mild hazard | 1 | 1 | 1 | Mild concern
Occupation / avocation | Moderate hazard | 2 | 1 | 2 | Moderate concern
Occupation / avocation | High hazard | 3 | 1 | 3 | Major concern
Driving record | Clean | 0 | 1 | 0 | No concern
Driving record | Minor violations only | 1 | 1 | 1 | Mild concern
Driving record | Repeated violations / recent issue | 2 | 1 | 2 | Moderate concern
Driving record | DUI / severe pattern | 3 | 1 | 3 | Major concern
Financial / application consistency | Fully consistent | 0 | 2 | 0 | No concern
Financial / application consistency | Minor discrepancy | 1 | 2 | 2 | Minor concern
Financial / application consistency | Noticeable inconsistency | 2 | 2 | 4 | Important concern
Financial / application consistency | Material under-disclosure / contradiction | 3 | 2 | 6 | Major concern
APS completeness | Complete APS | 0 | 2 | 0 | No concern
APS completeness | Small missing section | 1 | 2 | 2 | Mild uncertainty
APS completeness | Several missing details | 2 | 2 | 4 | Moderate uncertainty
APS completeness | Missing / unusable APS | 3 | 2 | 6 | Major uncertainty
Multiple comorbidities | None / isolated issue | 0 | 2 | 0 | No concern
Multiple comorbidities | Two mild conditions | 1 | 2 | 2 | Mild increase
Multiple comorbidities | Several meaningful conditions | 2 | 2 | 4 | Moderate increase
Multiple comorbidities | Several serious conditions | 3 | 2 | 6 | Major increase

## Bands
Min total score | Max total score | Risk band | Suggested underwriting action
0 | 10 | Low | Likely standard / preferred, subject to normal checks.
11 | 22 | Medium | Review needed, may require more evidence or clarification.
23 | 36 | High | Elevated risk, likely table rating / postponement / decline depending on rules.
37 | 37+ | Very high | Strong adverse risk; likely manual escalation or decline under many guidelines.